## Cover
GROUP 7
Service Charge App
WBS Estimate
Revision No. : | 1.0
Modified By - Date : | Tudtud, Lj Vincent - 2023/02/04
Preliminary Review and Approval - Date :
FInal Review and Approval - Date :

## Revision History
REVISION HISTORY
REV NO | MODIFIED BY | MODIFIED DATE | REMARKS | PRELIMINARY REVIEW AND APPROVAL | DATE REVIEWED | FINAL REVIEW AND APPROVAL | DATE APPROVED
1.0 | Tudtud, Lj Vincent | 2023-02-04 | Initial Creation

## Function List
MODULE | FUNCTION / DESCRIPTION / ASSUMPTIONS | TYPE | FUNCTIONAL CATEGORY |  |  |  | ESTIMATE (MD) | REMARKS
|  |  | SCREEN | REPORT | BATCH | OTHERS
Login Page |  |  | x
Forgot Password
Dashboard
List of tickets assigned to the user |  |  | x
Aging Tickets (assigned to current user) |  |  | x
Aging Tickets (all tickets, admin view) |  |  | x
Ticket Management
Ticket List |  |  | x
New Ticket |  |  | x
Email Notification | [5 empty] | x
Edit/Update Ticket | Only tickets assigned to the current user can be edited. |  | x
Attach File (Conforme Slip) | [5 empty] | x
Attach File (Proof of Payment) | [5 empty] | x
Attach File (Scanned OR Slip) | [5 empty] | x
Email Notification | [5 empty] | x
View Ticket |  |  | x
Add email reminder for aging tickets
Ticket Workflow | Please refer to Proposed Process Flow-AEES (Service Charges).pdf |  | x
Reports (With Excel/CSV Export)
Aging Tickets | List of aging open tickets |  |  | x
Monthly Report | How many new tickets, how many are ongoing and how many are closed.
Ticket List Per Asignee
Master Screens
User Management
List |  |  | x
Add email reminder for aging tickets |  |  | x
Edit |  |  | x
Delete |  |  | x
Role/User Type Management
List |  |  | x
Add |  |  | x
Edit |  |  | x
Delete |  |  | x

## Jumpstart Program Schedule
Lj Vincent Tudtud | Jeorge Ryan Lou | Cathleen Rose Gadiane | WBS | Task | Baseline Start | Baseline End | Days | Predecessors | Actual Start | Actual End
|  | * | 1 | Login Page
|  | * | 2 | Forgot Password
|  | * | 3 | Dashboard
|  | * | 4 | List of tickets assigned to the user
|  |  | 5 | Aging Tickets (assigned to current user)
|  |  | 6 | Aging Tickets (all tickets, admin view)
|  | * | 7 | Ticket Management
|  | * | 8 | Ticket List
|  | * | 9 | New Ticket
|  | * | 10 | Email Notification
|  | * | 11 | Edit/Update Ticket
|  |  | 12 | Attach File (Conforme Slip)
|  |  | 13 | Attach File (Proof of Payment)
|  |  | 14 | Attach File (Scanned OR Slip)
|  |  | 15 | Email Notification
|  | * | 16 | View Ticket
|  |  | 17 | Add email reminder for aging tickets
|  | * | 18 | Ticket Workflow
|  | * | 19 | Reports (With Excel/CSV Export)
|  |  | 20 | Aging Tickets
|  |  | 21 | Monthly Report
|  |  | 22 | Ticket List Per Asignee
|  |  | 23 | User Management
|  | * | 24 | List
|  |  | 25 | Add email reminder for aging tickets
|  | * | 26 | Edit
|  | * | 27 | Delete
|  |  | 28 | Role/User Type Management
|  | * | 29 | List
|  | * | 30 | Add
|  | * | 31 | Edit
|  | * | 32 | Delete